## HEC
|  |  | HEC - Action Items List |  |  |  | http://www.greece.org/hec/admin/
ID | Open Date | Task | Status | Due Date | Closed Date | Responsible | Notes
1 | 2015-02-20 | Fundraise letter | use template | 2015-03-21 | Closed | T,M,E
2 | 2015-02-20 | Grant Proposal | Create a generic GRANT proposal document | 2015-04-30 | OPEN | Terry | Look at he MSWord files here: http://www.greece.org/hec/admin/work/grants/
3 | 2015-02-22 | Bank account in Greece | Thanos to sent papers to Gus | *TBD* | OPEN | Gus, Thanos
4 | 2015-02-22 | P.O. Box in Greece | Thanos to sent papers to Gus | *TBD* | OPEN | Gus, Thanos
5 | 2015-02-22 | New Bank in USA | Opened HEC account at Bank of Am | *TBD* | 2015-05-07 | Thanos
6 | 2015-02-22 | PPA3 approval letter for pledge | Info was sent to Stelio | *TBD* | 2015-02-22 | Terry
7 | 2015-02-22 | Accomplishments 2013 | completed and posted on website | *TBD* | 2015-02-22 | Thanos
8 | 2015-02-22 | Accomplishments 2014 | completed and posted on website | *TBD* | 2015-02-22 | Thanos
9 | 2015-03-13 | Website | Update content - First page | *Ongoing* | OPEN | All
10 | 2015-03-13 | New server | Aqcuire a cloud web server fro Sysnet | *TBD* | OPEN | Thanos
11 | 2015-03-13 | Domain ClassicOlympics renewal |  | ASAP | Closed | G, T
12 | 2015-03-13 | HEC Corporation | Thanos will send all relevant docs to the team Review docs | 42301 | Closed | M, E, T, A
13 | 2015-04-18 | Adenda | Update Adenda to match bylaws | 2015-10-31 |  | All
14 | 2015-04-19 | Bylaws review & change | Complete Draft by Oct 31st. Vote is scheduled for 14Nov2015 | 2015-10-31 |  | Anna, Thanos, Eleni
15 | 2015-04-19 | Branding & PR |  | *TBD* |  | All
16 | 2015-04-19 | Google Analytics / search parameters |  | *TBD* |  | Gus, Thanos, Anna
17 | 2015-04-19 | Create Thraki2 | sandbox | 2015-04-19 | 2015-04-19 | Gus
18 | 2015-04-19 | Buy WP Thraki Theme |  | *TBD* |  | Gus
19 | 2015-04-19 | Upgrade to New PHP version |  | *TBD* |  | Thanos, Anna, Gus
20 | 2015-04-19 | Upgrade to New MySQL version |  | *TBD* |  | Thanos, Anna, Gus
21 | 2015-09-12 | Greeks.net | Connect with Jim for the xfer and payment | 2015-10-24 |  | Thanos
22 | 2015-09-12 | Thraceppa.org | currently hosted in Gus' private provider. Change the admin & contacts | 2015-11-28 |  | Gus, Anna, Thanos
23 | 2015-09-12 | Consolidate domains greece.org, ehk.gr, greeks.net, ClassicOlympics.org & .com, thraceppa.org |  | 2015-11-28 |  | Thanos, Gus
24 | 2015-09-12 | ehk.gr | Instal a basic WordPress and remove the current redirect | 2015-10-17 |  | Gus
25 | 2015-10-10 | jForms & Registration application | Joomla & jForms Consolidate databases for members | 2015-10-24 | 2015-11-02 | Nico, Thanos | http://www.greece.org/hec/registry-membership.php
26 | 2015-10-10 | Wikipedia | Resubmittal was again denied | 2015-10-31 |  | Gus, Thanos
27 | 2015-10-10 | Listserv license | Contact lSoft to get new LAK | 2015-10-20 | 2015-10-27 | Thanos, Anna
28 | 2015-10-10 | Assign a Social Media Lead | manage: fb page, fb group, Twitter, LinkedIn | 2015-10-17 |  | Thanos, Anna

## RACI
ID | Decision / Function / Activity R = Responsible (Doer) A = Accountable (Yes/No) C = Consulted I= Informed | Thanos | Anna | Eleni | Stelios | Fotini | Nico | Gus | Mario | Terry | Athanasios
1 | HEC Fundraising | A,C,I | A,C,I | C,I | C,I | C,I | C,I | C,I | C,I | R,A,C,I
2 | STEM Project | A,C,I | A,C,I | C,I | I | I | I | R,A,C,I | C,I | C,I
RACI Chart
Responsible: performs an activity or does the work
Accountable: ultimately accountable and has Yes/No authority
Consulted: contributes and send feedback to the activity.
Informed: person that needs to know of the decision or action

## STEM
STEM Project - Action Items List
ID | Open Date | Task | Status | Due Date | Closed Date | Responsible
1 | 2015-01-16 | meeting minutes | Completed meeting minutes | 2015-01-17 | 2015-01-17 | Eleni
2 | 2015-01-16 | Create a listserv mailing list | Created a mailing list based on WWII-Workgroup: stem@hec.greece.org | 2015-01-19 | 2015-01-19 | Anna
4 | 2015-01-16 | Create a website | Created a database wp_stem and Installed a fresh wordpress instance. Comleted the IIS configuration as: www.greece.org/stem | 2015-01-19 | 2015-01-19 | Thanos
8 | 2015-01-16 | A Process outline for the Project |  |  | OPEN | NYAS
9 | 2015-01-16 | Project Definition, Scope, and Goals |  |  | OPEN | Ioanna
10 | 2015-01-16 | Partner List, who can help. Identify non-profit organizations which can help |  |  | OPEN
11 | 2015-01-16 | HEC EC to discuss how to help and to recruit volunteers |  |  | OPEN
5 | 2015-01-17 | Website. Select a WP template and organize the website |  | 2015-01-31 | OPEN | Fotini, Gus
6 | 2015-01-18 | Create a Project Plan (MPP) | Need to define project milestones | 2015-01-31 | OPEN | Thanos, Ioanna
7 | 2015-01-20 | Publish the project/website via a global HEC email | Start working on email DRAFT | 2015-02-01 | OPEN | Anna, Thanos, Eleni
12 | 2015-01-21 | Maintain a web page in HEC with the Project's latest material |  | Ongoing | OPEN
13
14